## Sheet1
Start Date | End date | Description | Days | Date | Values | Milestone
2021-09-01 | 2021-09-30 | Thinking of senior project ideas | 30 | 2021-10-21 | 0 | import speech recognition
2021-10-01 | 2021-10-08 | Executive summary | 8 | 2021-10-21 | 1
2021-10-01 | 2021-10-05 | Research for voice recognition software | 5 | 2022-02-25 | 1 | Finish GUI
2021-10-18 | 2021-11-01 | Research about voice recognition, and python file handling | 15 | 2022-02-25 | 0
2021-11-01 | 2021-12-01 | Implementation of voice recognition | 31
2021-11-01 | 2021-12-01 | implementation of file searching | 31
2021-12-01 | 2021-12-08 | Research about application modification | 8
2021-12-08 | 2022-01-12 | implement application docking | 36
2022-01-13 | 2022-01-20 | Implementing a GUI | 8
2022-01-13 | 2022-01-28 | better file searching methods | 16
2022-02-07 | 2022-02-11 | implementing save messages | 5
2022-02-14 | 2022-02-17 | implementing way to mark the time | 4
2022-02-21 | 2022-02-28 | finish with GUI changes | 8
2022-03-22 | 2022-03-25 | changing how the program takes in info | 4
2022-03-25 | 2022-04-04 | ending | 11
2021-09-01 | 2022-04-04 | Entire seinor project | 216